## 🗂 Test Scenarios
Scenario ID | FR(s) Covered | Type | Scenario Name | Description | Priority | Status
TS-01 | FR-01 | UI | Register a New User with Correct Details | Check that a new user can sign up from the Register page and gets logged in automatically | High | Active
TS-02 | FR-09 | Negative | Registration Field Checks and Same Username | Check that registration works properly when required fields are empty, passwords don't match, and the username is already taken | Medium | Active
TS-03 | FR-01, FR-08 | UI | Create a New Account Successfully | Check that a new Savings or Checking account can be made using valid login and inputs | High | Active
TS-04 | FR-02, FR-03 | API | Account Shows Up in API After Creating from UI | Check that the account made from the UI can be fetched using GET /accounts with the right ID | High | Active
TS-05 | FR-04 | API | Check Account Type and Details from API | Check that the account type (SAVINGS/CHECKING), balance, and owner details coming from the API are correct | High | Active
TS-06 | FR-05 | UI | Transfer Money Between Accounts from UI | Check that money gets transferred properly between two of my own accounts using a valid amount | High | Active
TS-07 | FR-06, FR-07 | API | Check Balances Before and After Transfer | Get the balances from API before the transfer, do the transfer, then check the updated balances again | High | Active
TS-08 | FR-07 | API / Hybrid | Transfer Amount is Correct (Debit = Credit) | Check that the amount taken from the source account and added to the destination account is exactly the same as the transfer amount | High | Active
TS-09 | FR-01, FR-02, FR-03 | Hybrid | Create Account from UI and Check it in API | End to end: make an account from the UI, note down the account ID, then check it exists and has the right type using the API | High | Active
TS-10 | FR-09 | Negative | Access Without Login / Session Checks | Check that protected pages send users who are not logged in back to the login page, and the API blocks calls without proper access | Medium | Active
TS-11 | FR-06, FR-07 | Hybrid | Multiple Transfers Stay Consistent Across Accounts | Check that when we do many transfers one after another, all of them show up correctly in the API balances | Medium | Active

## 🧪 Test Cases
TC ID | Scenario ID | Type | Test Case Name | Description | Pre-conditions | Test Steps | Expected Result | Actual Result | Status | Remarks
TC-REG-UI-01 | TS-01 | UI | Register a New User with Valid Data | Check that a new user account gets created when we use valid registration details | ParaBank Register page is open (/parabank/register.htm) | 1. Open the Register page 2. Fill in First/Last Name, Address, City, State, Zip 3. Fill in SSN, a unique Username, Password and Confirm Password 4. Click 'Register' | Account gets created The message 'Your account was created successfully. You are now logged in.' is shown
TC-REG-UI-02 | TS-01 | UI | Check Auto-Login and Welcome After Registration | Check that the user who just registered is logged in automatically and sees a welcome | A new user was just registered (TC-REG-UI-01) | 1. Finish registration with valid data 2. Look at the page after clicking 'Register' 3. Check the header / menu state | 'Welcome <username>' is shown User is logged in (Log Out link is visible) Account Services menu can be opened
TC-REG-UI-03 | TS-02 | Negative | Registration – Required Fields Left Empty | Check that error messages come up when the required fields are left blank | Register page is open | 1. Open the Register page 2. Leave all the fields empty 3. Click 'Register' | Account is NOT created Errors are shown on the fields (e.g. 'First name is required.', 'Username is required.')
TC-REG-UI-04 | TS-02 | Negative | Registration – Password and Confirm Don't Match | Check that registration is stopped when Password and Confirm Password are not the same | Register page is open | 1. Fill in all valid details 2. Enter Password: Test@123 3. Enter Confirm Password: Test@999 4. Click 'Register' | Account is NOT created Error is shown: 'Passwords did not match.'
TC-REG-UI-05 | TS-02 | Negative | Registration – Already Used Username is Rejected | Check that the system does not allow registering with a username that already exists | We already know an existing username (e.g. john) | 1. Open the Register page 2. Fill in valid details 3. Enter Username: john (already exists) 4. Click 'Register' | Account is NOT created Error is shown: 'This username already exists.'
TC-AC-UI-01 | TS-03 | UI | Create a Savings Account – Valid Data | Check that a new SAVINGS account gets created with valid inputs | 1. User is logged in as john/demo 2. 'Open New Account' page is open | 1. Open the Open New Account page 2. Choose type: SAVINGS 3. Choose a from-account 4. Click 'Open New Account' 5. Note down the new Account ID from the success page | Account gets created New Account ID is shown 'Congratulations' message is shown
TC-AC-UI-02 | TS-03 | UI | Create a Checking Account – Valid Data | Check that a new CHECKING account gets created | 1. User is logged in 2. An existing account with money is available | 1. Open the Open New Account page 2. Choose type: CHECKING 3. Choose a from-account 4. Click 'Open New Account' 5. Note down the Account ID | CHECKING account gets created Account ID is shown Success message is shown
TC-AC-UI-03 | TS-03 | UI | Check the Success Message Content After Account Creation | Check that the correct text and account number are shown in the success message | User is logged in | 1. Create any new account 2. Look at the page after submitting | Page shows the 'Congratulations' confirmation and the 'Your new account number' label. The new account number is visible and is a valid positive number (not null/empty).
TC-TF-UI-01 | TS-06 | UI | Transfer Money – Valid Amount Between Two Accounts | Check that money transfers fine between two of my own accounts using a valid amount | 1. User is logged in 2. At least 2 accounts with enough balance are there | 1. Go to Transfer Funds 2. Enter amount: 100 3. Choose From Account 4. Choose a different To Account 5. Click Transfer | 'Transfer Complete!' message is shown From/To account details are shown on the page
TC-TF-UI-02 | TS-06 | UI | Transfer Confirmation Page Shows Correct Details | Check that the transfer confirmation page shows the correct from, to, and amount | User is logged in, 2 accounts are available | 1. Do a transfer of 200 2. Check what the confirmation page shows | Confirmation page shows: - Correct amount (200) - Correct From account - Correct To account
TC-API-01 | TS-04 | API | GET Accounts – HTTP 200 OK | Check that GET /accounts/{customerId} returns 200 with a valid JSON response | We have a valid customer ID (e.g. 12212) | 1. Hit GET /parabank/services/bank/customers/{customerId}/accounts 2. Check the HTTP status code 3. Check the response body | HTTP 200 OK Response body is a valid JSON array The array is not empty
TC-API-02 | TS-04 | API | New Account ID is Present in API Response | Check that the account ID created from the UI is there in the API accounts list | TC-AC-UI-01 is done, Account ID noted down from UI | 1. Hit GET /accounts for the customer 2. Go through the response array 3. Look for the noted Account ID | 200 OK The noted Account ID is found in the response array
TC-API-03 | TS-05 | API | Check the Account Type Field in API Response | Check that the 'type' field matches what was chosen while creating the account | Account created using TC-AC-UI-01 (SAVINGS) or TC-AC-UI-02 (CHECKING) | 1. Hit GET /accounts 2. Find the new account by ID 3. Read the 'type' field | 'type' is 'SAVINGS' or 'CHECKING' as per what was created Field is not null
TC-API-04 | TS-05 | API | Check Balance is a Number and Not Negative | Check that the balance field is a number (not a string) and is ≥ 0 | Account is there in the system | 1. Hit GET /accounts 2. Find the account 3. Check the 'balance' field's data type and value | 'balance' is a number (float/int) Balance ≥ 0 It is not returned as a string like '100.00'
TC-API-06 | TS-07 | API | Check Source Account is Debited After Transfer | Check that the source account balance goes down by exactly the transfer amount after the transfer | TC-API-05 is done (balance_before noted) TC-TF-UI-01 is done (transfer done) | 1. Hit GET /accounts again after the transfer 2. Get the source account balance 3. Compare it with src_balance_before | src_balance_after = src_balance_before − transfer_amount The difference is exact, no extra charges
TC-API-07 | TS-07 | API | Check Destination Account is Credited After Transfer | Check that the destination account balance goes up by exactly the transfer amount | dest_balance_before is noted, transfer is done from UI | 1. Hit GET /accounts after the transfer 2. Get the destination account balance 3. Compare it with dest_balance_before | dest_balance_after = dest_balance_before + transfer_amount No rounding errors
TC-API-08 | TS-08 | Hybrid | Transfer Debit Equals Credit (No Money Lost) | Check that the amount taken from the source is exactly equal to the amount added to the destination — no money lost or duplicated | Both before-balances are noted, transfer is done | 1. Calculate: src_before − src_after 2. Calculate: dest_after − dest_before 3. Check both values are equal and match the transfer amount | src_debit == dest_credit == transfer_amount No difference
TC-API-10 | TS-10 | Negative | GET Accounts – Wrong Customer ID Returns Error | Check that the API returns a 4xx error for a customer ID that does not exist | API is accessible | 1. Hit GET /accounts with a wrong customerId (e.g. 99999999) 2. Check the status code and response body | HTTP 404 or 400 Error message is present in the response body
TC-API-11 | TS-10 | Negative | GET Accounts – Access Without Auth Returns 401/403 | Check that the API rejects requests that have no authentication | API is accessible, no auth credentials are passed | 1. Hit GET /accounts without any auth header or session 2. Check the response | HTTP 401 or 403 Access is denied or 'Unauthorized' shows in the response
TC-E2E-02 | TS-09 | Hybrid | Create Account from UI → Check Type and Balance in API | Check that the account type and starting balance in the API match what was created on the UI | User is logged in, API is accessible | 1. Create a CHECKING account from UI 2. Note down the Account ID 3. Hit GET /accounts 4. Find the account → check type and balance | type == 'CHECKING' in API Balance ≥ 0 and is a number ID matches the ID shown on UI
TC-E2E-05 | TS-11 | Hybrid | Many Transfers in a Row – API Balances Stay Correct | Check that two transfers done one after another both show up correctly in the API balances | 3 accounts are available, user is logged in | 1. Note all balances from API (before) 2. Transfer 100 from A→B using UI 3. Transfer 50 from B→C using UI 4. Get the balances again from API 5. Check each change is exact | A went down by 100 B net change = +100−50 = +50 C went up by 50 Nothing is off
TC-NEG-03 | TS-10 | Negative | Access Transfer Funds Page Without Login | Check that a user who is not logged in cannot open the Transfer Funds page | User is NOT logged in (or the session is cleared) | 1. Go directly to /parabank/transfer.htm without logging in 2. See what the page does | User is sent to the login page Transfer Funds page cannot be opened
TC-NEG-04 | TS-10 | Negative | Login with Wrong Credentials | Check that the login page shows an error for a wrong username/password | ParaBank login page is accessible | 1. Enter username: wronguser 2. Enter password: wrongpass 3. Click Log In | Error: 'The username and password could not be verified.' User stays on the login page

## 🔗 RTM
REQUIREMENT TRACEABILITY MATRIX (RTM)
Requirement ID | Requirement Description | Test Scenario(s) | Test Case(s) | # TCs | Coverage Status
FR-01 | Create new account via UI | TS-01, TS-03, TS-09 | TC-REG-UI-01, TC-REG-UI-02, TC-AC-UI-01, TC-AC-UI-02, TC-AC-UI-03, TC-E2E-02 | 6 | ✅ Covered
FR-02 | GET accounts list via API | TS-04, TS-09 | TC-API-01, TC-API-02, TC-E2E-02 | 3 | ✅ Covered
FR-03 | Validate new account exists in API | TS-04, TS-09 | TC-API-01, TC-API-02, TC-E2E-02 | 3 | ✅ Covered
FR-04 | Validate account type and details in API | TS-05 | TC-API-03, TC-API-04 | 2 | ✅ Covered
FR-05 | Transfer funds via UI | TS-06 | TC-TF-UI-01, TC-TF-UI-02 | 2 | ✅ Covered
FR-06 | Validate updated balances using API | TS-07, TS-11 | TC-API-06, TC-API-07, TC-E2E-05 | 3 | ✅ Covered
FR-07 | Validate transfer applied correctly (before/after) | TS-07, TS-08, TS-11 | TC-API-06, TC-API-07, TC-API-08, TC-E2E-05 | 4 | ✅ Covered
FR-08 | Validate UI messages (success, confirmation) | TS-03 | TC-AC-UI-01, TC-AC-UI-02, TC-AC-UI-03 | 3 | ✅ Covered
FR-09 | Validate negative scenarios | TS-02, TS-10 | TC-REG-UI-03, TC-REG-UI-04, TC-REG-UI-05, TC-API-10, TC-API-11, TC-NEG-03, TC-NEG-04 | 7 | ✅ Covered
TOTAL: 9 Requirements ¦ 23 Test Cases ¦ ALL COVERED |  |  |  |  | ✅ 100%

## ▶ Execution Report
TEST EXECUTION REPORT — ParaBank Capstone
TC ID | Scenario ID | Type | Test Case Name | Executed By | Exec Date | Browser | Status | Actual Result | Defect ID | Evidence | Remarks
TC-REG-UI-01 | TS-01 | UI | Register a New User with Valid Data | Aaradhya Maharishi |  | Chrome | PASS | Account created and auto-logged in | — | Allure + trace | —
TC-REG-UI-02 | TS-01 | UI | Check Auto-Login and Welcome After Registration | Aaradhya Maharishi |  | Chrome | PASS | Welcome shown, session active | — | Allure + trace | —
TC-REG-UI-03 | TS-02 | Negative | Registration – Required Fields Left Empty | Aaradhya Maharishi |  | Chrome | PASS | Field errors shown, no account created | — | Allure + trace | —
TC-REG-UI-04 | TS-02 | Negative | Registration – Password and Confirm Don't Match | Aaradhya Maharishi |  | Chrome | PASS | 'Passwords did not match.' shown | — | Allure + trace | —
TC-REG-UI-05 | TS-02 | Negative | Registration – Already Used Username is Rejected | Aaradhya Maharishi |  | Chrome | PASS | 'This username already exists.' shown | — | Allure + trace | —
TC-AC-UI-01 | TS-03 | UI | Create a Savings Account – Valid Data | Aaradhya Maharishi |  | Chrome | PASS | Savings account created, ID shown | — | Allure + trace | —
TC-AC-UI-02 | TS-03 | UI | Create a Checking Account – Valid Data | Aaradhya Maharishi |  | Chrome | PASS | Checking account created, ID shown | — | Allure + trace | —
TC-AC-UI-03 | TS-03 | UI | Check the Success Message Content After Account Creation | Aaradhya Maharishi |  | Chrome | PASS | Congratulations + account number shown | — | Allure + trace | —
TC-TF-UI-01 | TS-06 | UI | Transfer Money – Valid Amount Between Two Accounts | Aaradhya Maharishi |  | Chrome | PASS | 'Transfer Complete!' shown | — | Allure + trace | —
TC-TF-UI-02 | TS-06 | UI | Transfer Confirmation Page Shows Correct Details | Aaradhya Maharishi |  | Chrome | PASS | From / To / amount correct | — | Allure + trace | —
TC-API-01 | TS-04 | API | GET Accounts – HTTP 200 OK | Aaradhya Maharishi |  | Chrome | PASS | 200 OK, non-empty JSON array | — | JSON log | —
TC-API-02 | TS-04 | API | New Account ID is Present in API Response | Aaradhya Maharishi |  | Chrome | PASS | Account ID found in response | — | JSON log | —
TC-API-03 | TS-05 | API | Check the Account Type Field in API Response | Aaradhya Maharishi |  | Chrome | PASS | type matches creation | — | JSON log | —
TC-API-04 | TS-05 | API | Check Balance is a Number and Not Negative | Aaradhya Maharishi |  | Chrome | FAIL | balance returned as string '100.00' | DEF-08 | JSON log + trace | Schema validation failure
TC-API-06 | TS-07 | API | Check Source Account is Debited After Transfer | Aaradhya Maharishi |  | Chrome | FAIL | Source dropped to 0 then negative, no block | DEF-03, DEF-06 | JSON log + trace | No min-balance; UI showed success
TC-API-07 | TS-07 | API | Check Destination Account is Credited After Transfer | Aaradhya Maharishi |  | Chrome | PASS | Destination credited by exact amount | — | JSON log | —
TC-API-08 | TS-08 | Hybrid | Transfer Debit Equals Credit (No Money Lost) | Aaradhya Maharishi |  | Chrome | FAIL | FROM stayed -384.5, TO +100; money created | DEF-02, DEF-06 | JSON log + trace | Debit ≠ credit on negative source
TC-API-10 | TS-10 | Negative | GET Accounts – Wrong Customer ID Returns Error | Aaradhya Maharishi |  | Chrome | PASS | 4xx returned for invalid ID | — | JSON log | —
TC-API-11 | TS-10 | Negative | GET Accounts – Access Without Auth Returns 401/403 | Aaradhya Maharishi |  | Chrome | FAIL | 200 OK returned without auth | DEF-04 | JSON log + trace | API not secured
TC-E2E-02 | TS-09 | Hybrid | Create Account from UI → Check Type and Balance in API | Aaradhya Maharishi |  | Chrome | PASS | type & balance match (textContent workaround) | DEF-07 | Allure + trace | #newAccountId hidden; used textContent()
TC-E2E-05 | TS-11 | Hybrid | Many Transfers in a Row – API Balances Stay Correct | Aaradhya Maharishi |  | Chrome | PASS | Each balance delta exact | — | JSON log | —
TC-NEG-03 | TS-10 | Negative | Access Transfer Funds Page Without Login | Aaradhya Maharishi |  | Chrome | FAIL | Stayed on transfer.htm, no redirect | DEF-05 | Screenshot + trace | Page not protected
TC-NEG-04 | TS-10 | Negative | Login with Wrong Credentials | Aaradhya Maharishi |  | Chrome | PASS | Error shown, stayed on login page | — | Screenshot | —
EXECUTION SUMMARY
Total Test Cases Executed | 23
Passed | 18
Failed | 5
Blocked | 0
Defects Logged | 8 (DEF-01 to DEF-08)
STATUS LEGEND → | PASS | FAIL | BLOCKED

## 🐛 Defect Report
DEFECT REPORT — ParaBank Capstone
Defect ID | TC ID | Defect Title | Description | Steps to Reproduce | Expected Result | Actual Result | Severity | Priority | Status | Evidence | Remarks
DEF-01 | — | Self-transfer allowed | Transfer to the same account is accepted; balance does not change. | 1. Login 2. Set From and To as the same account 3. Transfer 100 | Self-transfer blocked or validation error | Transfer accepted, balance unchanged, no error | Medium | P3 | Open | 07-balanceValidation (debug) | No dedicated test; found while debugging selectFrom(0)/selectTo(1)
DEF-02 | TC-API-08 | Money created from negative balance | Source stays negative but destination is still credited; money is created. | 1. Source balance = -384.5 2. Transfer 100 to another account 3. Check both balances | Transfer blocked, or debit = credit | FROM stayed -384.5, TO credited +100 | Critical | P1 | Open | 10-fundTransfer.spec.ts (TS-08) | —
DEF-03 | TC-API-06 | No minimum balance enforcement | Account can drop to 0 and go deeply negative with no block. | 1. Transfer full / over balance 2. Repeat across tests 3. Check balance | Block when funds insufficient / below minimum | Balance dropped to 0, then negative, no block | High | P2 | Open | 07-balanceValidation.spec.ts (TS-07) | —
DEF-04 | TC-API-11 | API accessible without auth | GET Accounts returns data without authentication. | 1. Call GET /accounts with no auth 2. Check status code | 401 or 403 | 200 OK with account data | Critical | P1 | Open | 08-accountsNegative.spec.ts (TS-10) | Clean repro with assertion
DEF-05 | TC-NEG-03 | Transfer page accessible without login | transfer.htm opens without an active session. | 1. No login / clear session 2. Open /parabank/transfer.htm | Redirect to login page | URL stayed on transfer.htm | High | P1 | Open | 05-negativeScenarios.spec.ts (TS-10) | Clean repro with assertion
DEF-06 | TC-API-08, TC-API-06 | "Transfer Complete!" shown on silent backend failure | UI shows success but balance is unchanged. | 1. Do a transfer 2. UI shows 'Transfer Complete!' 3. Re-check balance via API | Error shown if transfer not applied | Success message shown, balance unchanged | High | P1 | Open | 10-fundTransfer.spec.ts (TS-08); 07-balanceValidation.spec.ts (TS-07) | —
DEF-07 | TC-E2E-02 | #newAccountId element CSS-hidden | New account ID element is hidden; innerText() returns empty. | 1. Create account via UI 2. Read #newAccountId via innerText() | Account ID readable via innerText() | innerText() empty; textContent() required | Low | P3 | Open | 09-createAccount.spec.ts (TS-09); 06-accounts.spec.ts (TS-04) | Automation workaround used
DEF-08 | TC-API-04 | Balance Returned as String Type | API returns 'balance' as string '100.00' instead of numeric 100.0 | 1. Login as john/demo 2. Create new account 3. Call GET /accounts 4. Inspect 'balance' field type | balance should be numeric (float) | balance returned as String: '100.00' | Medium | P2 | Open | — | Schema validation failure
SEVERITY GUIDE | Critical – System crash / data loss | High – Major feature broken | Medium – Partial feature issue | Low – Cosmetic / minor